## Cover
CONTRACT APPRECIATION DOCUMENT
(CAD)
CWG
Subcontractor
Prepared By : Sign:
Checked By: Sign:
Approved By: Sign:

## Index
INDEX
SR. NO. | CONTENTS / CLAUSES RELATED TO | PAGE NO.
1 | SCOPE OF WORK | 1 | - | 10 | 9 | 10
2 | SALIENT FEATURES OF CONTRACT | 11 | - | 20 | 9 | 10
3 | IMPORTANT SUBMITTALS & DUE DATES | 21 | - | 30 | 9 | 10
4 | SUBMITTALS RELATED TO PRICING DOCUMENTS | 31 | - | 39 | 8 | 9
5 | INSURANCES | 40 | - | 42 | 2 | 3
6 | PAYMENT | 43 | - | 50 | 7 | 8
7 | PRICE ADJUSTMENT | 51 | - | 52 | 1 | 2
8 | VARIATION | 53 | - | 57 | 4 | 5
9 | TAXATION | 58 | - | 58 | 0 | 1
10 | NOTICE | 59 | - | 68 | 9 | 10
11 | EOT AND COST CLAUSES | 69 | - | 71 | 2 | 3
12 | CONTRACTOR'S DUTIES AND RESPONSIBILITIES | 72 | - | 85 | 13 | 14
13 | ENGINEER'S/EMPLOYER'S DUTIES AUTHORITIES AND RESPONSIBILITIES | 86 | - | 96 | 10 | 11
14 | DEFAULT OF CONTRACTOR / EMPLOYER AND TERMINATION | 97 | - | 99 | 2 | 3
15 | GENERAL OBSERVATION | 100 | - | 110 | 10 | 11
16 | EMPLOYER'S CLAIM AND RECOVERIES | 111 | - | 115 | 4 | 5
17 | PROCEDURE FOR CLAIMS | 116 | - | 116 | 0 | 1
18 | SETTLEMENT OF DISPUTE | 117 | - | 118 | 1 | 2

## Scope
Sr. No. | Scope
i.)
ii.)
iii.)
iv.)
v.)
vi.)
vii.)
viii.) |  |  | 2015-05-12
ix.)
x.)
xi.)
xii.)
xiii.)
xiv.)
xv.) |  | 2003 | #REF!
xvi.) |  | 2003
xvii.)
xviii.)
xix.)
xx.)
xxi.)
xxii.)
xxiii.)
xxiv.)
xxv.)
xxvi.)
xxvii.)
xxviii.)
xxix.)
xxx.)
xxxi.)
xxxii.)
xxxiii.)
xxxiv.)
xxxv.)
xxxvi.)
xxxvii.)
xxxviii.)
xxxix.)
xl.)
xli.)
xlii.)
xliii.)
xliv.)
xlv.)
xlvi.)
xlvii.)
xlviii.)
xlix.)
l.)
li.)
lii.)
liii.)
liv.)
lv.)
lvi.)
lvii.)
lviii.)
lix.)
lx.)
lxi.)
lxii.)
lxiii.)
lxiv.)
lxv.)
lxvi.)
lxvii.)
lxviii.)
lxix.)
lxx.)
lxxi.)
lxxii.)
lxxiii.)
lxxiv.)
lxxv.)
lxxvi.)
lxxvii.)
lxxviii.)
lxxix.)
lxxx.)
lxxxi.)
lxxxii.)
lxxxiii.)

## Salient Features
0
SALIENT FEATURES OF CONTRACT
Sr. No. | Description of Clause | Clause No. | Observations
1 | Name and address of the Employer
2 | Name and address of the Engineer
3 | Contractor
4 | ParticipationShare in Joint Venture
5 | Source of Funds
6 | Letter of Acceptance
7 | Accepted Contract Amount
8 | Base Date |  |  |  | 2015-05-12
9 | Commencement of Works
10 | Time for Completion
11 | Defect Notification Period
12 | Key Dates & Liquidated Damages
13 | Limit of Liquidated Damages
14 | Bonus Payment
15 | Language for Communication |  |  | 2003 | #REF!
16 | Law of the Contract |  |  | 2003
17 | Performance Security
18 | Time for Access to Site
19 | Mobilization Advance
20 | Plant & Machinery Advance
21 | Interest on Advance Payment
22 | Limitation in Advance payment
23 | Start repayment of advance payment
24 | Repayment amortisation of advance payment
25 | Payment for materials when delivered to site
26 | Retention money
27 | Lieu of Retention
28 | Limit of Retention Money
29 | Payment of Retention Money
30 | Issue of Interim Payment Certificate
31 | Payment of Interim Payment Certificate
32 | Issue of Final Payment Certificate
33 | Payment of Final Payment Certificate
34 | Currency of Payment
35 | Interest for delayed payments
36 | Amount of insurance for design (Professional Indemnity Insurance
37 | Insurance cover for Contractor’s All Risk and other requirements as specified in the GCC
38 | Amount of third party insurance

## Access To Site
0
Location / Drawing Reference | Description | Area (m2) | Type | Access Date from Commence ment of the Works No. of Days | Access Date | Vacate Date from Commence ment of the Works. No. of Days | Note
2016-07-18

## Key Dates
Rating | Key Dates | Description | Number of Days from Commencement | Completion Date | Delay Damages for non achievement of key Dates | Remarks
50.5828 | 13th January 2022 | Agreement Date
47.3345 | 13th January 2022 | Effective Date
47.3345 |  | Expiration Date
44.6392 | This Tender Bond is valid for 90 calendar days from ……………….. {date of tender submission} to ……………… and renewable before expiry for a further 30 calendar days if requested in writing by the Employer . | Renewal Term
44.6392 | This Tender Bond is valid for 90 calendar days from ……………….. {date of tender submission} to ……………… and renewable before expiry for a further 30 calendar days if requested in writing by the Employer . | Notice Period To Terminate Renewal

## Important Submittals
Rating | Description of Clause | Submittals | Due Date | Observations
58.0495 | Document Name | CONTRACT AGREEMENT

## Submittals Pricing Docs
Sr No | Submittals | SOP Reference No | Clause No. | Due Date | Observations
1 | Performance Security
2 | Submission of Evidence of Insurances
3 | Copies of the Insurance Policies
4 | Initial Work Programme
5 | Expanded and detailed version of initial Work Programme
6 | Revised programme
7 | Revised programme to ensure or to be consistent with the completion by the Key Dates
8 | Three Months Rolling Programme |  |  |  |  | 2016-07-18 | 2016-11-06
9 | Progress Reports
10 | Design Submission Programme
11 | Up-dated version of Design Submission Programme
12 | Design Quality Plan and Delivery Schedule
13 | Quality Plan
14 | Manufacturing Quality Plan and Delivery Schedule
15 | proposed Quality Management System
16 | Supplement to the Site Quality Plan
17 | Interface Management Plan & Interface Management Programme
18 | Interface Performance Audits
19 | Master Interface Matrix and Interface Coordination Sheets
20 | Station Coordination Installation Plan for Each Station on a Room by Room Basis
21 | Project Management Information System
22 | Staff Organisation Plan
23 | Proposed Occupational Health, Safety and Environmental Plan
24 | Detailed and comprehensive contract-specific Safety Plan
25 | Report of external audit
26 | OHS&E Manual Requirement Submission (monthly Environmental Management Reports)
27 | Detailed and comprehensive Site Environmental Plan (Environmental Management Plan to include Spoils Management, Diesel Emission Mitigation & Dust Control Plan & Audits)
28 | Comprehensive Testing & Commissioning Programmme
29 | Schedule of spare parts
30 | Training Plan
31 | Plan reviews and updates
32 | Schedule of internal, consultant, subcontractor and supplier audits
33 | Inspection Test Plan
34 | Factory Test Plan
35 | Partial Acceptance Test Plan
36 | System Acceptance Test Plan
37 | Maintenance support plan
38 | Software support plan
39 | Backup copies of the software
40 | Site accommodation for the Engineer’s staff
41 | Installation Plan and Programme
42 | Method Statement for Installation
43 | General layout plan for construction plant & equipment
44 | Drawings showing the locations of major facilities, including the Contractor’s, Employer’s and Engineer’s site offices
45 | Detailed Cashflow Estimate
46 | Status of all designs checked during the preceding month
47 | Written proposal for the use and occupation of these Site and works Areas
48 | Design Certificate for Temporary works:
49 | The Existing Building Survey Report
50 | Utility Diversion Plan
51 | Proposals showing the layout of Traffic Management
52 | Number and format of the required document submissions

## Submission Format
Submittal | No. of Paper Copies |  |  | No. of Electronic Copies | Reference
| A1 | A3 | A4
Initial Programme and Works Programme plus supporting information and narrative
Monthly Programme Update
Three Month Rolling Programme
Three Week Rolling Programme
Monthly Progress Report
Preliminary and Definitive Designs
Construction Reference Drawings
Works Drawings
Method Statements
Interface Management Plan
As built drawings
Materials Submissions (documentation)
Operation and Maintenance Manuals
E&M Submissions
Quality Plan
Quality Control Register
Reports of Quarterly Quality Audits
Materials and Workmanship Test Results/Reports
Safety Plan
Environmental Plan
Traffic Management Submissions
Investigation and survey reports.
Monitoring, protection and replacement proposal reports.
All other submittals
Notes:
i) In case of any contradiction between the text and this table then the text shall prevail,unless otherwise instructed by the Engineer.
ii) Drawings to support A4 text documents shall be of A3 size.
A: 20/23

## Insurance
Rating | Description of Clause | Observations
41.3058 | Insurance | The Tenderer is notified that the contractual insurances, to be prov ided by the successful Tenderer under the provisions of the Conditions of Contract, shall be fr om an appr oved insurance comp any in the Dubai . The ins urance company and the insurance policies shall be subject to the approval of the Employer.

## Payment
Rating | Description of Clause | Observations
39.128 | Revenue/Profit Sharing | 10% of the Accepted Contract Amount As stated in Particular Conditions of Cont ract As stated in L etter of Acceptance AED 13,660 .00 per day 10% of the final Contract Price (*)
39.0539 | Minimum Commitment | TWO MILLION FOUR HUNDRED FIFTY-EIGHT THOUSAND THREE HUNDRED FORTY-TWO ONLY 2,458,342.00/-

## Price Adjustment
Rating | Description of Clause | Observation
39.0539 | Volume Restriction | For the purposes o f implementation and interpretation o f this Clause overtime p eriods are any periods in excess of eight (8) normal working daylight hours a day on Monday to Satur day inclusive of any week, or six (6) normal working daylight hours on a day Monday to Saturday inclusive during the month of Ra madan, and all day Sunday of any week and all day on any recognised public ho liday.

## Variation
Rating | Description of Clause | Observations
39.0539 | Ip Ownership Assignment
39.0539 | Joint Ip Ownership
39.0539 | License Grant
38.8654 | Non-Transferable License | Except as provided under Sub -clause 4.4 [Subc ontractors], Contractor shall not assign or transfer all or any of its rights or oblig ations under this Contract, nor shall any share or interest therein in any manner or degree be transferred or assigned by Contractor, directly or indirectly, without the prior consent in writing of Employer.
38.3157 | Source Code Escrow

## Taxation
Rating | Description of Clause | Observations
39.4398 | Uncapped Liability | Th e liability of the Contractor shall in any event be limited to the cost of rectification of the Works.

## Notices
Rating | Description of Clause | Notice | Notice Regarding | Observation
39.593 | Termination For Convenience
38.801 | Post-Termination Services |  |  | After a not ice of termination under Sub -Clause 16.2 [Termination by Contractor] has taken effect, the Employer shall promptly: a. Return the Performance Secu rity to the Contractor b. Pay the Contractor in acco rdance wit h Sub-Clause 19.6 [Option al Termi nation, Payment and Relea se].
41.3058 | Covenant Not To Sue

## EOT,COST Clause
Sr. No. | Clause No. | Description of Clause | EOT | COST | Observations
GCC
PCC
PCC
PCC
GCC

## Res n Duties-Contractor
Rating | Description of Clause | Observations
39.593 | No-Solicit Of Customers
39.593 | No-Solicit Of Employees

## Res n Duties-EmployeeEngineer
Rating | Description of Clause | Responsibility & Authority pertains to | Observations

## Default of Contractor Employee
Rating | Description of Clause | Observations
40.6102 | Liquidated Damages

## General
Rating | Description of Clause | Observations
41.601 | Governing Law | The Contract shall be governed by the laws of the Emirate of Dubai and the federal laws of the United Arab Emirates.
41.3058 | Third Party Beneficiary

## Employer Claim
Rating | Description of Clause | Observations
39.8046 | Audit Rights | The Employer reserves the right to audit any aspect of the system.

## Claim Proced
Rating | Description of Clause | Observations

## Dispute Settlement
Rating | Description of Clause | Observations
41.601 | Most Favored Nation | The Employer shall not bi nd himself to accept the lowest or any Tender and shall not state a reason for the acceptance or rejection of a Tender.
39.593 | Competitive Restriction Exception
39.593 | Rofr/Rofo/Rofn | The Employer shal l be free to accept which ever Tender he may select.